## UAT_Results
UAT plan and results
Simulated workflow on real GLEIF entity data. Not Citi data. Automated cases were run on 2026-10-06 (50 passed). Yellow cells are for you to fill after running the manual and document cases.
ID | Area (JD requirement) | Scenario | Input | Expected result | Method | Reference | Actual result | Pass/Fail | Tester | Date
UAT-01 | Rules and verification | R01 fires for a non-ISSUED record | Entity status LAPSED; then ISSUED; then ANNULLED | Fires for LAPSED only; does not fire for ISSUED or ANNULLED | Automated pytest | tests/test_rules.py::test_r01 | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-02 | Rules and verification | R02 renewal overdue | ISSUED with a passed renewal date; ISSUED with a future date; LAPSED with a passed date | Fires only for ISSUED with a passed date | Automated pytest | tests/test_rules.py::test_r02 | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-03 | Rules and verification | R03 inactive entity | Entity status INACTIVE; entity status ACTIVE | Fires only for INACTIVE | Automated pytest | tests/test_rules.py::test_r03 | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-04 | Rules and verification | R04 country mismatch | Legal country differs from HQ country; same country | Fires only when they differ | Automated pytest | tests/test_rules.py::test_r04 | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-05 | Rules and verification | R05 no parent and no exception | Missing parent with no reporting exception; otherwise | Fires only for the unexplained missing parent | Automated pytest | tests/test_rules.py::test_r05 | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-06 | Sanctions and country risk | R06 name score at or above 80 | A list name and a non-matching name | Fires only at a score of 80 or above (potential match for review) | Automated pytest | tests/test_rules_screen.py::test_r06 | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-07 | Sanctions and country risk | R07 FATF country | Entity in a FATF-listed country; entity elsewhere | Fires only for a listed country | Automated pytest | tests/test_rules_screen.py::test_r07 | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-08 | Rules and verification | Stored rule hits equal the rule SQL | Compare fact_rule_hit with the shared rule definitions | Counts match exactly | Automated pytest | tests/test_rules.py::test_built_hits_match_shared_rules | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-09 | Verification and authorization | Maker is never the checker | Every request in the simulation | No request has the same maker and checker | Automated pytest | tests/test_workflow.py::test_maker_is_never_the_checker | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-10 | Accuracy | Completed plus open equals received | Whole simulated request table | No request lost or double counted | Automated pytest | tests/test_workflow.py::test_completed_plus_open_equals_received | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-11 | Accuracy | Completion is not before receipt | Every completed request | Completion time is never earlier than receipt time | Automated pytest | tests/test_workflow.py::test_completion_is_not_before_receipt | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-12 | Accuracy | Every request points to a real entity | Join requests to dim_entity | No request has an unknown entity | Automated pytest | tests/test_workflow.py::test_every_request_points_to_a_real_entity | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-13 | Verification and authorization | Error truth is kept out of the request table | Inspect request table columns | Injected-error truth is not visible to the workflow | Automated pytest | tests/test_workflow.py::test_error_truth_is_kept_out_of_the_request_table | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-14 | Verification and authorization | Every logged exception exists in the truth table | Compare fact_exception with sim_error_truth | No exception without a matching injected error | Automated pytest | tests/test_workflow.py::test_every_logged_exception_exists_in_the_truth_table | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-15 | Deadlines | Turnaround matches an independent recompute | Recompute turnaround in Python | SQL and Python agree | Automated pytest | tests/test_metrics.py::test_turnaround_matches_python | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-16 | Deadlines | SLA breaches match an independent recompute | Recompute breaches in Python | SQL and Python agree | Automated pytest | tests/test_metrics.py::test_sla_breach_matches_python | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-17 | Deadlines | Queue bands follow the rule | Open requests in the work queue | Each request is in the correct priority band | Automated pytest | tests/test_metrics.py::test_queue_bands_follow_the_rule | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-18 | Deadlines | Queue is complete, unique and ordered | Open requests in the work queue | Every open request appears once, in order | Automated pytest | tests/test_metrics.py::test_queue_is_complete_unique_and_ordered | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-19 | Escalation | Escalation counts match an independent recompute | Recompute escalations in Python | SQL and Python agree | Automated pytest | tests/test_metrics.py::test_escalation_matches_python | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-20 | Deadlines | Priority queue serves the earliest due first | Queue with mixed due times | Earliest due time is served first | Automated pytest | tests/test_scenarios.py::test_priority_serves_earliest_due_first | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-21 | Deadlines | FIFO queue serves in arrival order | Queue with mixed arrival times | Arrival order is respected | Automated pytest | tests/test_scenarios.py::test_fifo_serves_in_arrival_order | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-22 | Accuracy | Baseline scenario reproduces the workflow tables | Compare baseline scenario with fact_request | Same completed and open counts (1,980 and 20) | Automated pytest | tests/test_scenarios.py::test_baseline_scenario_reproduces_the_workflow_tables | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-23 | Data protection | Screening table stores no names | Inspect fact_screen columns | No company name is stored | Automated pytest | tests/test_rules_screen.py::test_fact_screen_stores_no_names | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-24 | Accuracy | Same seed gives the same tables | Run the workflow twice with the same seed | Identical tables | Automated pytest | tests/test_workflow.py::test_same_seed_gives_same_tables | Passed in the full run: python -m pytest tests -q gave 50 passed (no failures). | Pass | Automated (pytest) | 2026-10-06
UAT-25 | Verification and authorization | Checker equal to the maker is rejected | Checker_Log, row 2 (maker M3): type M3 in checker_id | Excel shows the 'Maker-checker rule' error and refuses the entry | Manual Excel | Checker_Log, cell D2 |  | Not run
UAT-26 | Verification and authorization | A different checker is accepted | Checker_Log, row 2: type C1 in checker_id, then clear it | C1 is accepted with no error | Manual Excel | Checker_Log, cell D2 |  | Not run
UAT-27 | Deadlines | Priority bands match hours left | Daily_Queue, all 20 rows | Rows under 72 h show P2; later rows show P3; none overdue | Manual Excel | Daily_Queue, columns F and G |  | Not run
UAT-28 | Deadlines | Overdue request turns red | Test on a COPY of the workbook: set one due time in the past | The row turns red. Do not save the change in the real file | Manual Excel | Daily_Queue, conditional format |  | Not run
UAT-29 | Lodgment | Lodged without a complete check is flagged | Lodgment_Log, row 17 | Red flag 'CHECK: lodged without complete check' | Manual Excel | Lodgment_Log, row 17 |  | Not run
UAT-30 | Archiving | Archived while incomplete is flagged | Archive_Manifest, incomplete row | Red flag 'CHECK: archived while incomplete' | Manual Excel | Archive_Manifest |  | Not run
UAT-31 | Accuracy | Overall KPI check shows ALL OK | Open KPI_Summary | B2 says ALL OK and every Check cell says OK | Manual Excel | KPI_Summary, cell B2 |  | Not run
UAT-32 | Accuracy | Total in bands equals open requests | KPI_Summary, ageing table | Total in bands is 20 and its check says OK | Manual Excel | KPI_Summary, band table |  | Not run
UAT-33 | Accuracy | LEI column shows the full 20-character code | Data_Requests, lei column | No code is cut off or shown in scientific format | Manual Excel | Data_Requests, column lei |  | Not run
UAT-34 | Accuracy | Dropdown lists work | Click action_status in Daily_Queue and the status and type columns in the logs | A dropdown arrow appears and lists the allowed values | Manual Excel | Daily_Queue, Checker_Log, Lodgment_Log |  | Not run
UAT-35 | Staying current | Reg_Watch blank-status check is OK | Open Reg_Watch | 'Blank status' shows 0 and OK; REG04 describes the R02 SLA change | Manual Excel | Reg_Watch, rows 8 and 10 |  | Not run
UAT-36 | Documentation | Footer carries the simulated label | Print preview of KPI_Summary | Footer reads 'Simulated workflow on real GLEIF entity data. Not Citi data.' | Manual Excel | KPI_Summary, print preview |  | Not run
UAT-37 | Escalation | Follow the R02 route in the matrix | Read SOP-ESC-01 v1.1 for rule R02 | Handled by Maker then Team Lead, escalate to Operations Manager, SLA 24 h | Document review | SOP-ESC-01 v1.1, matrix |  | Not run
UAT-38 | Escalation | R06 is handled as a potential match only | Read SOP-ESC-01 v1.1 and QRY-01 for R06 | Route goes to Compliance (simulated); no client reply mentions screening | Document review | SOP-ESC-01 v1.1, QRY-01 |  | Not run
UAT-39 | Documentation | Change log shows the R02 change | Compare SOP-R02-01 v1.0 and v1.1 | v1.1 shows SLA 48 h to 24 h under CR-001 and the documents affected | Document review | SOP-R02-01 v1.0 and v1.1 |  | Not run
UAT-40 | Documentation | A second person can follow the signatory procedure | Give SOP-SIG-01 and the workbook to a second person to process one signatory change | They complete the change using only the procedure and the workbook | Document review | SOP-SIG-01 v1.0 |  | Not run

## Summary
UAT summary
Total cases | 40
Passed | 24
Failed | 0
Not run | 16
Automated cases | 24
Manual Excel cases | 12
Document review cases | 4
Check: passed + failed + not run = total | OK
A failed case is a finding. Record it in the Actual result column and log the fix; do not delete or hide it.